## Slide 2: Key Activities
Start | End | Label
August 26, 2024 | December 23, 2024 | Gathering data from our Target audience and Hiring Companies
August 26, 2024 | December 23, 2024 | Connecting with Universities, academic institutions and OPDs.
October 21, 2024 | January 18, 2025 | Team building and Hiring
October 28, 2024 | January 10, 2025 | Team Capacity Building
November 4, 2024 | February 1, 2025 | Delivering computers which will be used by beneficiaries
October 21, 2024 | January 28, 2025 | Curriculum Design and Review
December 16, 2024 | January 29, 2025 | Accreditation Process
December 20, 2024 | January 9, 2025 | Call for application, selection process and pre-bootcamp trainings
January 13, 2025 | February 26, 2025 | Starting for pre-bootcamp trainings in Web Development Fundamentals Academy

## Slide 3: Milestones
Date |  | Label
December 23, 2024 |  | Data Gathering for Target Audience and Hiring Companies
December 23, 2024 |  | Finding a pool of potential program candidates
January 9, 2025 |  | Material acquisition
January 29, 2025 |  | Conclusion of Curriculum Design & Getting accreditation
February 26, 2025 |  | Start of SheCanCODE DSE Bootcamp - Cohort 1
August 29, 2025 |  | Graduation of COHORT 1